## OSG open AP's
MNP OSG ACTIONS LOG - OPEN ACTIONS
AP # | Description | Date initiated | Owner | Status
ACTIONS ADDED AFTER CENERVA SERVICE START DATE (1 AUGUST 2018)
AP59 | Investigate impact of per port charge changes | 2018-10-04 | Cenerva | Open
AP61 | OSG members to read and comment on Cenerva Inception Report | 2018-10-04 | All | Open
AP79 | Cenerva to prepare recommendation for website update and refresh | 2019-01-10 | Cenerva | Open
AP89 | Cenerva to record OSG approval of the Change Request and promulgate the approved changes to the Manual. | 2019-04-25 | Cenerva | Open
AP96 | Cenerva to contact Syniverse re inaccurate invoices and POs. | 2019-04-06 | Cenerva | Open

## OSG completed APs
MNP OSG ACTIONS LOG - CLOSED ACTIONS
AP # | Description | Date initiated | Owner | Status
AP1 | Share your scores for the OSG tender so that we can progress with the offer |  | Magnus, Ian | Completed
AP2 | Commence discussions with FCS and facilitate the contract once we make a group decision |  | Magnus, Ian | Completed
AP3 | Update OSG on the handover from Alex |  | Gretel/Dani | Completed
AP4 | Decide who will be OSG Chair for July |  | All | Completed
AP5 | Attend UK MNP Purchasers review budgetary pricing proposal meeting |  | All | Completed
AP6 | Ask Cenerva to send draft contract for discussion |  | Magnus | Completed
AP8 | Set up OSG calls for July - replaced by Monday 10:00 |  | Gulistan | Completed
AP9 | Set up ORG meetings |  | Gretel | Completed
AP10 | Request a new quote from Syniverse |  | Catherine | Completed
AP11 | CP letter to Ofcom re authentication |  | Gulistan | Completed
AP12 | Justin to speak to Anne |  | Justin | Completed
AP13 | Gulistan or Barry to speak to Shaun |  | Barry | Completed
AP14 | Ask FCS to be the custodian of OSG confidential information and review Cenerva contract |  | Magnus | Completed
AP15 | Agree any relevent reason to reject PAC codes - get an agreed OSG view |  | All | Completed
AP16 | Gretel to pick up AP 15 at next weeks ORG - + agenda item on right to refuse |  | Gretel | Completed
AP17 | Review of ~ compensation process for PAC and N-PAC - await further clarity from Industry group |  | All | Completed
AP18 | Gretel - had response from - Vectone(Mundio) changed SFTP - Vodfone and O2 could yet be change IP address for Mundio/Vectone |  | Gretel | Completed
AP19 | SMS routing issues with Vectone - SMS - 2nd stage (first focus on IP changes) |  | All | Completed
AP20 | Check Process manual to ensure process of changing IP's included - left for Cenerva to address |  | All | Completed
AP21 | Port autolocking - Industry/ ORG - include on agenda - Clarity needed -( H3G signed up to auto locking) but not all industry supporting mandatory Locking |  | All | Completed
AP22 | Industry Technical Weeking - needs feedback from attendees |  | All | Completed
AP23 | O2 to host next meeting in Slough - has data been set ? 13th July and then 27th ? |  | Ian | Completed
AP24 | Industry Meeting - Angela Kefford (EE) - Chair for July and then Ian (O2) shall chair for August |  | Ian | Completed
AP25 | Chase up Chris at Cinerva re proposed agreement |  | Magnus | Completed
AP26 | Work towards having Cinerva with signed agreement within Eary Aug 18 |  | All | Completed
AP27 | OSG memebers to consdier implications and back plans for if can not arrive at quick agreement with Cinerva |  | All | Completed
AP28 | All OSG Members agree that invoice/fee's process continue as normal and any rebates resolved next budget process |  | All | Completed
AP29 | All OSG members to check internally with account departments as to paying FCS invoices |  | All | Completed
AP30 | Next OSG Call - Monday 30th July - August OSG chair hand over Magnus to Ian |  | All | Completed
AP31 | Request call between FCS and Cinerva post OSG -> FCS breifing/agreement |  | Magnus | Completed
AP32 | Check MNP Production Mgr email in box |  | Dani/Gretel | Completed
AP33 | OSG to provide dates and contact points for working group meetings |  | OSG | Completed
AP34 | OSG to provide documents on unresolved auto-switch implementation issues |  | OSG | Completed
AP35 | Cenerva to produce a report on OSG operations, including auto-switch readiness |  | Cenerva | Completed
AP36 | OSG to provide handover notes to Cenerva |  | OSG | Completed
AP37 | Cenerva to facilitate regular Monday morning OSG calls |  | Cenerva | Completed
AP38 | OSG members to respond individually to Cenerva information request of 17 July |  | OSG members individually
AP39 | Cenerva to set meeting schedule through to August 2019 |  | Cenerva | Completed
AP40 | Cenerva to obtain contract progress report from FCS |  | Cenerva | Completed
AP42 | Cenerva to schedule meeting and call with Syniverse to progress Syniverse proposal | 2018-08-13 | Cenerva | Completed
AP43 | OSG to agree position on Syniverse proposed SLAs on 20 August call | 2018-08-13 | Cenerva + OSG | Completed
AP44 | Cenerva to be provided passwords for all areas of the website and other OSG - Cenerva to check with Danielle and OSG will contact Alex if necessary | 2018-08-13 | Cenerva + OSG | Completed
AP45 | Cenerva (Nicholas) to liaise with BT (Barry), BT Connect (Magnus) and FCS (Louise) to develop current list of FCS membershiip | 2018-08-13 | Nicholas | Completed
AP41 | Vodafone to invite Cenerva to meeting re SMS validation scheduled for 14 August | 2018-08-13 | Vodafone | Completed
AP46 | Cenerva (Nicholas) to liaise with EE (Gretel) to coordinate next steps on port autoocking (see also AP21) | 2018-08-13 | Nicholas and Gretel | Completed
AP47 | Cenerva (Nicholas) to liaise with EE (Gretel) and O2 (Ian) to decide next steps re Plan Mobile complaint | 2018-08-13 | Nicholas, Gretel and Ian | Completed
AP48 | Cenerva (Nicholas) to liaise with EE (Gretel) re Virgin Mobile requirement for encrypted e-mails | 2018-08-13 | Nicholas and Gretel | Completed
AP49 | GDPR risks and issues to be considered as part of Syniverse review | 2018-08-13 | All | Completed
AP50 | Cenerva to research and report on SMS validation methods overseas | 2018-08-14 | Cenerva | Completed
AP51 | OSG to respond to Ofcom letter of 31 July setting out our position on SMS validation | 2018-08-14 | Cenerva | Completed
AP52 | BT/EE to provide illustrations and examples of fraud risk associated with un-validated SMS PAC route | 2018-08-21 | BT/EE | Completed
AP53 | Cenerva to obtain OSG agreement to release of OSG/Syniverse MNP oontract | 2018-08-21 | Cenerva and OSG | Completed
AP54 | Cenerva to establish google drive resource for sharing of auto-switch documentation | 2018-08-21 | Cenerva | Completed
AP55 | Cenerva will circulate the agenda for the 13 September OTG and ORG on 10 September. | 2018-09-06 | Cenerva | Completed
AP56 | Cenerva to investigate Syniverse change request process (note syniverse penalties to be included) | 2018-08-24 | Cenerva | Completed
AP57 | OSG members to push FCS to accelerate completion of the contract and payment of outstanding invoices | 2018-10-04 | All | Completed
AP58 | Three to pursue the recurring fee reduction request with Syniverse. | 2018-10-04 | Three - Catherine | Completed
AP60 | OTG and ORG distribution and invitation lists to be reviewed. | 2018-10-04 | Cenerva - Nicholas | Completed
AP62 | Vodafone to investigate and report on continuing repatriation issues | 2018-10-04 | Vodafone - Rob | Completed
AP63 | EE to investigate and report on Orange repatriation issues | 2018-10-04 | EE - Gretel | Completed
AP64 | Xmas porting days and arrangements to be clarified and communicated asap | 2018-10-04 | Cenerva | Completed
AP65 | Comment on Syniverse change request by 19 October | 2018-10-15 | System owners | Completed
AP66 | Propose penalties framework for Syniverse | 2018-10-15 | System owners | Completed
AP67 | OSG members to provide any comments on the Syniverse response and draft Change Request. Cenerva to issue commissioning e-mail for this. | 2018-11-06 | OSG mmbers | Completed
AP68 | Cenerva to clarify to Syniverse that the proposed penalties framework should apply to the full system set-up cost (i.e. £240k). | 2018-11-06 | Cenerva | Completed
AP69 | Cenerva to clarify with Syniverse that whether they would invoice each of the system owners for their contribution of the 25% initial system set up charge. | 2018-11-06 | Cenerva | Completed
AP70 | Cenerva to raise question with Syniverse about migration to a UK data centre if needed. | 2018-11-06 | Cenerva | Completed
AP71 | O2 to raise Plan Comms responses re fraudulent ports | 2018-11-06 | O2 - Ian | Completed
AP73 | OSG members to provide any comments on draft PAC/STAC/INFO rejection reasons letter by close of business 11 Jan. | 2019-01-10 | All | Completed
AP72 | Cenerva to riase ongoing repatriation issue with Vodafone | 2018-11-06 | Cenerva | Completed
AP73 | Cenerva would draft proposed acceptable wording on indemnities and refunded fees in the event that the contract is terminated early. | 2018-11-06 | Cenerva | Completed
AP74 | Cenerva and OSG would push FCS for payment of outstanding invoices to Cenerva. | 2018-11-06 | All | Completed
AP75 | OSG members to comment to Cenerva on Syniverse draft change request by close 23 Nov | 2018-11-19 | EE, O2, Three, Voda | Completed
AP76 | Three to contact Vodafone re any ongoing repatriations issues. | 2019-01-10 | Three | Completed
AP76 | Cenerva to provide written explanation of these clarification points to OSG members. | 2018-12-06 | Cenerva | Completed
AP72 | Cenerva to draft amendments to the PAC/STAC/INFO rejection reasons letter to Ofcom. | 2019-01-10 | Cenerva | Completed
AP74 | Cenerva to circulate the consumer information document to OSG members. | 2019-01-10 | Cenerva | Completed
AP75 | Cenerva to provide detail to O2 on ongoing Vectone issues. | 2019-01-10 | Cenerva - Nicholas | Completed
AP78 | Cenerva to cancel the 14 January OSG catch-up meeting | 2019-01-10 | Cenerva | Completed
AP80 | Cenerva to contact Syniverse for status of Exit Report. | 2019-02-07 | Cenerva | Completed
AP77 | EE to e-mail Cenerva (cc other Executive Members) re PAR backlogs. | 2019-01-10 | EE - Gretel | Completed
AP82 | Cenerva to arrange conference call asap with representatives from EE, VF, O2 & Three – to gather further details – which will be then discussed as an Agenda item at the OTG/ORG session on 13 February 2019 | 2019-02-07 | Cenerva | Completed
AP83 | Cenerva to cancel Monday, 11 February OSG catch-up meeting, however remaining catch-up meetings to remain in the diary. | 2019-02-07 | Cenerva | Completed
AP87 | Cenerva to circulate Ofcom request for agenda items (for 19 March round table meeting) | 2019-03-07 | Cenerva | Completed
AP84 | OSG members to review Change Request and draft UK Mobile Switching and Service Termination Process Manual and provide comments to Cenerva by 22 March. | 2019-03-07 | All | Completed
AP85 | Cenerva to schedule Change Request as formal business at the 4 April Administrative Committee meeting. | 2019-03-07 | Cenerva | Completed
AP86 | Cenerva to communicate need for information sharing at the auto-switch Test Forum meeting on 12 March, and report back to OSG. | 2019-03-07 | Cenerva | Completed
AP88 | Virgin Mobile to codes spreadsheet | 2019-03-07 | Faisal | Completed
AP90 | OSG AC members to consider O2 proposal Cenerva to meet Ofcom for to understand plan and objectives. | 2019-04-25 | OSG AC members | Completed
AP91 | OSG AC members to consider budget and Cenerva proposal and revert to Cenerva. | 2019-04-25 | OSG AC members | Completed
AP92 | Cenerva to brief Virgin Mobile on conclusion of discussions with DCPW | 2019-04-06 | Cenerva | Completed
AP93 | Cenerva to write to Ofcom on behalf of OSG re the common database proposal. | 2019-04-06 | Cenerva | Completed
AP94 | Cenerva to offer mid-June meeting/call to brief Ofcom on auto-switch preparedness, and enquire about Ofcom auto-switch publicity plans | 2019-04-06 | Cenerva | Completed
AP95 | OSG members to conduct final review of 2019/20 budget and Cenerva proposal. | 2019-04-06 | OSG AC members | Completed

## OSG risk register
MNP OSG risk register
No. | Description | Potential impact | Mitigation method | RAG status | Resolution date
BAU RISKS
R1 | Cenerva contract with FCS not yet completed | No legal underpinning for delivery of services by Cenerva | Chase FCS for completion of their contract review - Re |  | 2018-12-06
R2 | Incomplete documentation for Cenerva integration and handover | Negative impact on Cenerva service delivery | Meetings and ongoing discussion between Cenerva and OSG colleagues
R3 | Need for improved reporting from OTG ORG PMWG to AC | Lsck of transparency and escalation | Cenerva to provide regular OTG and ORG reports, discuss PMWG framework with Delegated Reps
R4 | Need for improved transparency of Syniverse information and performance | Insufficient tracking of the system | Cenerva to put in place programme with Syniverse
R5 | MNP OSG websie requires significant improvement | Inadequate resource for industry | Reform of website as medium term priority
AUTO-SWITCH RISKS
ASR1 | No agreed Customer validation method for SMS auto-switch requests | Delay to full implementaion of auto-switch. | Ofcom confirmed they will not change the GC requirement for 60 second PAC provision. Each operator now working unilaterally on authentication.
ASR2 | Tight testing window for auto-switch | Delay to full implementaion of auto-switch, or not fully tested | Ongoing management and tracking of service development and testing issues with Synyverse
ASR3 | Insufficient oversight and governance by MNP OSG of auto-switch implemnentation work | Issues and potential issues not flagged and /or escalated quickly enough | Cenerva to create governance and regular reporting framework
ASR4 | Document sharing respources needed. | Slows discussion or problems with version control | Cenerva to establish resource for sharing of auto-switch documentation - now in place |  | 2018-12-06
ASR5 | Delays to contract amendment with Syniverse | Delays auto-switch implementation | Drive agreement with Syniverse and re-set schedule. Change request now agreed. |  | 2018-12-06
ASR6 | Patchy industry collaboration with programme manager | Risk of incomplete implementation and compliance | Cenerva engaging with each of the main providers
ASR7 | Senior auto-switch owner in each of the major network companies | Slow decision making and escalation | Cenerva to keep under review
ASR8 | Testing approach is for minimum inter-network testing | incomplete testing of consumer experience may mean there are problems at launch | Industry has accepted this as a risk. 07/03/2019 agreed that Cenerva would remind industry of need for comprehensive testing - see AP86